## Sheet1
Date Submitted | Name | Project Address | Type of Application | Description | Status | Planner
2012-09-25 | Martin Fenlon | 498 Woodland | MCUP 12-04/SUP 12-03 | Demo/remodel, new Second Unit | Met with applicant on 5/5/15. Pending resubmittal of plans. Elaine Aguilar sent applicant email to schedule a meeting, per his request, and has not heard back as of 10/21/15. | VG
2012-11-13 | CETT Invest. | 630 Baldwin Ct. | HDP 12-02 / CUP 12-09 | Stonegate - construction 3,512 SF home | PC Workshop held on March 6, 2014. Revised plans submitted on 3/3/2015, comment letter provided to applicant on 06.01.15. Applicant provided reply to comments by email on Aug. 11, and staff requested revised plans to review, which applicant submitted on May 10, 2016. Staff provided comment letter on 07.25.16. | VG
2012-11-13 | CETT Invest. | 638 Baldwin Ct. | HDP 12-03 / CUP 12-10 | Stonegate - construction 3,528 SF home | PC Workshop held on March 6, 2014. Revised plans submitted on 3/3/2015, comment letter provided to applicant on 06.01.15. Applicant provided reply to comments by email on Aug. 11, and staff requested revised plans to review, which applicant submitted on May 10, 2016. Staff provided comment letter on 07.25.16. | VG
2014-01-14 |  | 576 Elm | Pre-Application Review | New 2-story single-family residence exceeding 4,000 SF | Conducted pre-application review meeting; pending submittal of HDP application for Planning Commission review. | VG
2014-08-12 |  | 11 Nathaniel Terrace | HDP 14-01/CUP 14-05 | Stonegate - Construction of new 4,392 sq.ft. SFR | Project went to PC on August 20, 2015, continued to date uncertain. | VG
2014-12-01 |  | Stonehouse Vesting Tentative Tract Map No. 65348 | VTTM 14-01 | Tract Map subdivision including 9 new lots. | Staff provided incomplete letter to applicant, pre-development meeting occurred on Feb. 3, 2015. Applicant addressing comments. Applicant resubmitted on May 30, 2017, incomplete letter issued on June 29, 2017. | VG
2015-12-24 |  | 9 Nathaniel Terrace | HDP 14-02/CUP 14-08 | Stonegate - Construction of new 4,377 sq. ft. SFR | Notice of incomplete application sent to applicant on 01/22/15. Materials submitted to applicant on 3/19/2015. Notice of incomplete application sent 4/17/15. | VG
2015-01-06 |  | 15 Nathaniel Terrace | HDP 15-01/CUP 15-01 | Stonegate - Construction of new 6,126 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Resubmitted 3/19/2015. NOI sent to applicant 4/17/15. Resubmitted 05/10/16, NOI sent 06/09/16. | VG
2015-01-06 |  | 603 Baldwin Ct | HDP 15-02/CUP 15-02 | Stonegate - Construction of new 3,593 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Resubmitted 3/19/2015, NOI sent to applicant 4/17/15. Resubmitted 06/07/16, NOI sent 07/06/16. | VG
2015-01-06 |  | 605 Baldwin CT | HDP 15-03/CUP 15-03 | Stonegate - Construction of new 4,572 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Resubmitted 3/19/2015, NOI sent to applicant 4/17/15. Resubmitted 06/07/16, NOI sent 07/06/16. | VG
2015-01-06 |  | 707 Baldwin Ct | HDP 15-04/CUP15-04 | Stonegate - Construction of new 4,561 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Applicant submitted materials 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. Resubmitted, NOI sent 08/30/16. | VG
2015-01-06 |  | 710 Baldwin Ct | HDP 15-05/CUP 15-05 | Stonegate - Construction of new 5,009 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Applicant submitted materials 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. Resubmitted, NOI sent 08/30/16. | VG
2015-01-06 |  | 608 Baldwin Ct | HDP 15-06/CUP 15-06 | Stonegate - Construction of new 4,525 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Applicant submitted materials 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. Resubmitted, NOI sent 08/30/16. | VG
2015-01-08 |  | 600 Baldwin Ct | HDP 15-07/CUP 15-07 | Stonegate - Construction of new 4,309 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Applicant submitted materials 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. Resubmitted, NOI sent 08/30/16. | VG
2015-01-08 |  | 660 Baldwin Ct | HDP 15-08/CUP 15-08 | Stonegate - Construction of new 4,940 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15. Applicant submitted materials 3/23/2015. Notice of incomplete application sent to applicant 4/22/15. Resubmitted, NOI sent 08/30/16. | VG
2015-01-08 |  | 700 Baldwin Ct | HDP 15-09/CUP 15-09 | Stonegate - Construction of new 5,529 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/5/15.Applicant submitted materials 3/23/2015. Notice of incomplete application sent to applicant 4/22/15. Resubmitted, NOI sent 08/30/16. | VG
2015-01-21 |  | 63 Carter Ave | HDP 15-10/CUP 15-10 | Stonegate - Construction of new 2,952 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/19/15. Applicant submitted materials 3/19/2015. Notice of incomplete application sent to applicant 4/22/15. | VG
2015-01-21 |  | 718 Baldwin Ct | HDP 15-11/CUP 15-11 | Stonegate - Construction of new 5,420 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/19/15. Applicant submitted materials 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. | VG
2015-01-21 |  | 61 Carter Ave | HDP 15-12/CUP 15-12 | Stonegate - Construction of new 3,239 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/19/15. Applicant submitted materials 3/23/2015. Notice of incomplete application sent to applicant on 4/22/2015. | VG
2015-01-21 |  | 59 Carter Ave | HDP 15-13/CUP 15-13 | Stonegate - Construction of new 3,225 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/19/15. Applicant submitted materials 3/23/2015. Notice of incomplete application sent to applicant 4/22/15. | VG
2015-01-29 |  | 720 Baldwin Ct | HDP 15-14/CUP 15-14 | Stonegate - Construction of new 3,310 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/27/2015. Applicant submitted materials on 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. | VG
2015-01-29 |  | 620 Baldwin Ct | HDP 15-15/CUP 15-15 | Stonegate - Construction of new 3,529 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/27/2015. Applicant submitted materials on 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. Resubmitted on 09/15/16, staff reviewing for completeness. | VG
2015-01-29 |  | 716 Baldwin Ct | HDP 15-16/CUP 15-16 | Stonegate - Construction of new 4,993 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/27/2015. Applicant submitted materials on 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. Resubmitted, NOI sent on 08/30/16. | VG
2015-01-29 |  | 730 Baldwin Ct | HDP 15-17/CUP 15-17 | Stonegate - Construction of new 2,898 sq. ft. SFR | Notice of incomplete application sent to applicant on 2/27/2015. Applicant submitted materials on 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. | VG
2015-02-05 |  | 738 Baldwin Ct | HDP 15-18/CUP 15-19 | Stonegate - Construction of new 3,467 sq. ft. SFR | Notice of incomplete application sent to applicant on 3/5/2015. Applicant submitted materials on 3/19/2015. Notice of incomplete application sent to applicant 4/17/15. Notice of incomplete application sent to applicant on 11.21.16. | VG
2015-02-19 |  | 7 Nathaniel Terrace | HDP 15-19/CUP 15-20 | Stonegate - Construction of new 6,375 sq. ft. SFR | Currently under review for application completeness. Applicant submitted materials 3/23/2015. Notice of incomplete application sent to applicant 4/22/15. | VG
2015-03-05 |  | 1 Nathaniel Terrace | HDP 15-20/CUP 15-21 | Stonegate - Construction of new 4,235 sq. ft. SFR | Application submitted on 3/5/15. Notice of incomplete application sent to applicant on 4/2/15. | VG
N/A |  | Citywide | Priority Water Conservation Policies | Study, review, and consideration to implement various water conservation policies during water moratorium period (up to 31 policies for consideration and ranked from 1-3 in priority) | Various policies to be agendized for City Council meetings within the next 9 months | Staff
2015-04-27 |  | 150 S Baldwin Ave | SUP 15-01/ CUP 16-01 | Add 2nd unit with attached garage. Second unit is 756 sq. ft. and attached a garage is 310 sq. ft. In addition, add 88 sq. ft to the existing garage. | CUP approved on May 5, 2016. SUP notices mailed out by staff on 05.23.16 to initiate the 20-day comment period. Staff emailed covenant to applicant on 06.17.16, needs to sign and notarize prior to building permit issuance. Staff notified applicant that proposed changes to covenant are not acceptable to city attorney on 12.07.16. | VG
2015-06-15 |  | St. Rita's Parish 318 N Baldwin | Pre-Application Review | Master Plan | Staff met with applicant on 08.11.15 to review comment letter. RFP for traffic study released on Jan. 15, 2015, Gibson Transportation selected, doing parking counts week of 0303.21.16. Vincent and Bruce met with consultant to discuss traffic study scope. | VG
11/30+A32:F35/2016 |  | 190 E. Mira Monte | SUP 16-05 | Second Unit Permit for 646 s.f 2nd unit | 11.30.16 - applicant submitted, staff reviewing for completeness 12/20/16 - Incomplete letter to applicant , awaiting resubmital. 11/20/17 - Applicant resbumitted plans. Reviewing for completeness 12/13/17 - Application deemed complete. 12/19-17 - Courtesy notice sent to adjacent property owners, comment period ends on 1/15/18 1/18/18 - Comment period ended, staff working on covenant for 2nd unit | JP
2016-12-12 |  | 94 N. Baldwin Ave. | CUP 16-05 | Convert existing bldg. into restaurant/tea room use in the Commercial Zone. | 11.30.16 - applicant submitted, staff reviewing for completeness 12/20/16 - Incomplete letter to applicant 06/05/17 Applicant resubmitted, staff reviewing for completeness. Incomplete letter issued on 07/06/17. Applicant resubmitted on 09/28/17, staff reviewing for completeness. Incomplete letter issued on 10.17.17. Applicant resubmitted on Nov. 21, staff reviewing. Application complete, PC hearing scheduled for 01/18/18. PC approved, Reso being drafted for next PC meeting. | LC
2017-04-27 |  | 193 Oak Meadow | CUP 17-01 | To demo existing SFR and construct a 3,503 sq.ft. residene and 297-sq.ft. workshop addition to existing garage. Total sq.ft. exceeds CUP threshold. | Staff reviewing application for completeness. 05/10/17 Incomplete letter sent to applicant on 05.10.17. 3/2018 (As of) - Applicant still has not resbumitted, will follow up with Vincent on who he wants to take over project? | VG
2017-07-19 |  | 91 E. Orange Grove | DRP 17-03 & DDP 17-03 | Dem existing house, construct new 6,794 sf home. | 7/19/17 - staff reviewing application for completeness 8/17/17 - Incomplete Letter sent to applicant, awaiting ressubmit | JP
2017-08-01 |  | 124 E. Alegria Avenue | DRP 17-01 | Enclose porches, add 152 sq.ft., add 565 sq.ft. garage | Staff reviewing application for completeness. 08.24.17 Sent incomplete letter to applicant. 3/2018 - Applicant has yet to resbumit anything. Will follow up with Vincent on who he wants to take over project? | VG
2017-09-28 |  | 62 E. Carter Ave. | DRP 17-06 & DDP 17-04 | DRP to allow new 2,352 sq.ft. SFR and DRP to demo existing patio structure. | Staff reviewing for completeness. Letter of incomplete application emailed to applicant on 10.26.17. 2/2018 - Applicant resbumitted , Clare taking over project. 3/9/18 - staff sent incomplete letter. 4/3 Staff sent incomplete letter | CL
|  | Citywide | Zone Change & GPA | Zoning Map update & Land Use Map revision | Staff preparing maps prior to scheduling PC meeting | VG
|  | Citywide | Municipal Code Text Amendment 17-07 | Nonconforming Uses Ordinance Amendment | First PC meeting on 08.03.17, returning on 08.17.17, 10.19.17, 11.02.17. PC public hearing scheduled for Dec. 14, 2017 for recommendation to CC. CC 1st Reading - 02/24/18. CC 2nd Reading - 3/27/18. Ordinance effective date 4/29/18. | VG
2017-11-14 |  | 240 E. Sierra Madre BLvd. | DRP 17-05 & DDP17-06 | Two story addition including bedroom & bath, and two car garage at rear of existing residence. DDP is needed to allow demolition of rear wall for access to new addition | 11/14/17 -Staff is reviewing the application for completeness 12/12/17 - Incomplete letter sent to applicant. 12/18/17 - Applicant resbumitted corrections. Staff reviewing 1/18/18 - Applicant resbumitted corrections. Planning Commission approved project at 4/5/18 meeting. | JP
2018-01-18 |  | 325 W. Grandview Ave. | DRP 18-01, ADRP 18-01 | Demo existing 844 residence and detached 365 sf 2 car garage, replace with new 2 story 2,762 sf residence and 926 sf partial basement 2 car garage with laundry/work room. | 1/18/18 - staff reviewing application for completeness 2/15/18 - Staff sent incomplete letter, still awaiting resbumit | JP
2018-02-01 |  | 120 W. Sierra Madre Blvd | CUP 18-01 | CUP for full alcohol service (Sierra Fusion) | 3/15/18 - staff sent complete letter. 4/5/18 Application approved by Planning Commission. | CL
2018-03-06 |  | 659 W. Alegria Ave | SUP 18-01, ADRP 18-02 | Converting existing garage to second unit and new carport | 3/7/18 - staff sent incomplete letter 3/21 complete letter. 3/23-4/12/2018 notice period. | CL
2018-03-15 |  | 125 E. Mira Monte Ave. | DDP 18-02 & CA 18-02 | Demolish 14 linear feet of an exterior wall to accommodate an interior remodel and 186 SF addition. | 2/7/18 - Staff sent complete letter March 1, 2018 - Planning Commission approves project with conditions. Plan check submitted on 3/19/18. | VG
|  | Citywide | Municipal Code Text Amendment 18-01 | Commercial Zone Ordinance Amendments | First PC meeting on 3/15/18. Returning to PC on 4/19/18 for further discussion. | VG
PC - Planning Commission
HDP - Hillside Development Permit
CUP - Conditional Use Permit
MVAR - Minor Variance
SUA - Second Use Permit Amnesty
MCUP - Minor Conditional Use Permit
MMW - Minor Modification to Wireless Facility
TPM - Tentative Parcel Map
MCTA - Municipal Code Text Amendment
CA - Certificate of Appropriateness
DDP - Discretionary Demolition Permit